## Sheet2
PROPOSED AFPSLAI ID CARD IMPLEMENTATION TIMELINE
ID | TASK | Duration (Working days) | Start | Finish | Dependencies | Responsible Unit | REMARKS
1 | Notice of Award | 1 day | 3/9/17 | 3/9/17 |  | AFPSLAI
2 | Submission of Proposed Project Timeline | 1 day | 3/9/17 | 3/9/17 | Task ID 1 | ALLCARD
3 | Approval of Timeline | 4 days | 3/9/17 | 3/13/17 | Task ID 2 | AFPSLAI
4 | Technical Meeting - Finalization of Software Functional Specifications and Test plan for the UAT | 1 day | 3/14/17 | 3/14/17 | Task ID 1 | AFPSLAI, ALLCARD
5 | MOA Signing | 1 day | 3/17/17 | 3/17/17 | Task ID 3 & 4 | AFPSLAI, ALLCARD
6 | Biling of 50% down Payment | 1 day | 3/17/17 | 3/17/17 | Task ID 5 | ALLCARD | Payment in 15 days upon billing?
7 | Posting of Performance bond | 1 day | 3/20/17 | 2017-03-20 | Task ID 5 | ALLCARD
8 | Submission of Test Plan | 1 day | 3/20/17 | 2017-03-20 | Task ID 4 | ALLCARD
9 | Approval of Test Plan | 1 day | 3/24/17 | 3/24/17 | Task ID 8 | AFPSLAI
10 | System Development / Customization | 14 days | 3/25/17 | 4/7/17 | Task ID 9 | ALLCARD
11 | USER ACCEPTANCE TESTING(UAT) | 5 days | 4/8/17 | 4/12/17 | Task ID 10 | AFPSLAI, ALLCARD
12 | Approval / Sign-off of UAT | 1 day | 4/18/17 | 4/18/17 | Task ID 11 | AFPSLAI
13 | Delivery of ALL Hardware & Software components to AFPSLAI HO | 45 days | 3/18/17 | 2017-05-01 | Task ID 5 &12 | ALLCARD
14 | Training Manila | 2 days | 5/3/17 | 5/4/17 | Task ID 13 | AFPSLAI, ALLCARD
15 | Training CEBU | 2 days | 5/9/17 | 5/10/17 | Task ID 13 | AFPSLAI, ALLCARD
16 | Project Completion and Acceptance Sign-off | 1 day | 5/12/17 | 5/12/17 | Task ID 13,14,15 | ALLCARD
16 | Billing 50% balance | 1 day | 5/12/17 | 5/12/17 | Task ID 13,14,15 | ALLCARD | Payment in 15 days upon billing?

## Sheet1
AFPSLAI ID CARD IMPLEMENTATION TIMELINE | [5 empty] | ANNEX 'B'
ID | TASK | DURATION (Calendar days) | START | FINISH | DEPENDENCIES | RESPONSIBLE UNIT | REMARKS
1 | Notice of Award | 1 day | 3/9/17 | 3/9/17 |  | AFPSLAI
2 | Technical Meeting - (part 1) Finalization of Software Functional Specifications and Test plan for the UAT | 1 day | 3/14/17 | 3/14/17 | Task ID 1 | AFPSLAI, ALLCARD
3 | Technical Meeting - (part 2) Finalization of Software Functional Specifications and Test plan for the UAT | 1 day | 2017-03-24 | 3/24/17 | Task ID 1 | AFPSLAI, ALLCARD
4 | Submission of Proposed Project Timeline | 1 day | 4/3/17 | 4/3/17 | Task ID 1 | ALLCARD
5 | Submission of revised MOA | 1 day | 4/3/17 | 4/3/17 | Task ID 1 | ALLCARD
6 | Approval of Timeline | 4 days | 4/3/17 | 4/6/17 | Task ID 2 | AFPSLAI
7 | Approval of revised MOA | 3 days | 4/3/17 | 4/6/17 | Task ID 3 | AFPSLAI
8 | MOA Signing | 1 day | 4/10/17 | 4/10/17 | Task ID 4,5,6 & 7 | AFPSLAI, ALLCARD
9 | Posting of Performance bond | 1 day | 4/17/17 | 4/17/17 | Task ID 8 | ALLCARD
10 | Biling of 50% down Payment | 1 day | 4/17/17 | 4/17/17 | Task ID 8 | ALLCARD | Payment in 5 days upon billing
11 | Submission of Test Plan | 1 day | 4/17/17 | 4/17/17 | Task ID 6 & 7 | ALLCARD
12 | Approval of Test Plan | 1 day | 4/17/17 | 4/17/17 | Task ID 11 | AFPSLAI
13 | System Development / Customization | 14 days | 4/17/17 | 5/4/17 | Task ID 12 | ALLCARD
14 | USER ACCEPTANCE TESTING(UAT) | 15 days | 5/4/17 | 5/19/17 | Task ID 13 | AFPSLAI, ALLCARD
15 | Approval / Sign-off of UAT | 1 day | 5/11/17 | 5/11/17 | Task ID 14 | AFPSLAI
16 | Delivery of ALL Hardware & Software components to AFPSLAI HO | 45 days | 4/10/17 | 5/25/17 | Task ID 6,7 &15 | ALLCARD
17 | Training Manila | 2 days | 5/25/17 | 5/26/17 | Task ID 16 | AFPSLAI, ALLCARD
18 | Training CEBU | 2 days | 5/29/17 | 5/30/17 | Task ID 16 | AFPSLAI, ALLCARD
19 | Project Completion and Acceptance Sign-off | 1 day | 5/31/17 | 6/1/17 | Task ID 16,17,18 | ALLCARD
20 | Billing 50% balance | 1 day | 6/2/17 | 6/2/17 | Task ID 16,17,18 | ALLCARD | Payment in 5 days upon billing